## Sheet1
Feature | Description | State | Duration
Product list | show list of product in the home page | Open | 2 | Time | 35
Filter Component | filter products based on their sizes and sort by price | Open | 2 | Rate | 30 | USD/Hrs
Cart Component | show selected items in the cart on the right sidebar | Open | 3 | Cost | 1050 | USD
Add Animation | Animated product list and adding to cart | Open | 2
Add Model | Show model when user click on a product | Open | 2
Checkout Form | Show checkout form to get buyer data | Open | 2
Products Backend | Create a simple backend to send products to frontend | Open | 3
Add Redux | Create store, initial state and reducer and redux devtools | Open | 2
Add Redux To Products | Move product state to redux | Open | 3
Add Redux To Filter | Move filter state to product | Open | 3
Add Redux To Cart | Move cart state to redux | Open | 3
Create Order | Handel frontend and backend of creating an order | Open | 3
Add Admin Section | Use react-router to create two routes for Home and Admin | Open | 2
Publish on Heroku | Create Mongodb atlas database and publish Heroku app | Open | 3